## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Kalaipriya | 2026-08-31 | Apache comments dataset could not be read because some fields exceeded the default CSV field size limit | Sprint 1 | Kalaipriya | Maintainability | Increased the CSV field size limit before processing the dataset. | 2026-08-31 | Closed | Apache dataset processing completed successfully.
2 | Kalaipriya | 2026-09-01 | Embedding generation required additional processing time for historical bug data | Sprint 1 | Kalaipriya | Maintainability | Used batch processing for embedding generation and completed FAISS indexing. | 2026-09-02 | Closed | Embeddings and vector indexing completed successfully.
3 | Kalaipriya | 2026-08-28 | Bug log file upload initially required endpoint implementation to support multipart file input. | Sprint 1 | Kalaipriya | Standards | Implemented the file upload endpoint using FastAPI UploadFile and File. | 2026-08-29 | Closed | File upload tested successfully with a sample .log file.
4 | Kalaipriya | 2026-09-03 | Triage classification required careful condition handling for different bug descriptions. | Sprint 2 | Kalaipriya | Maintainability | Refined rule-based conditions and tested severity, priority and affected component classification. | 2026-09-03 | Closed | Triage Agent validated successfully
5 | Kalaipriya | 2026-09-04 | Stack trace formats varied across different test cases | Sprint 2 | Kalaipriya | Maintainability | Added parsing logic to identify exception type, failure point and affected code path. | 2026-09-04 | Closed | Log Analysis Agent validated successfully
6 | Kalaipriya | 2026-09-05 | Agent outputs needed to be combined before passing context to downstream agents. | Sprint 2 | Kalaipriya | Standards | Integrated Triage and Log Analysis outputs into a combined agent context. | 2026-09-05 | Closed | Multi-agent context flow validated successfully.
7 | Kalaipriya | 2026-09-15 | Duplicate detection agent was matching candidate defect against itself when querying vector database, yielding a false 1.0 similarity duplicate. | Sprint 3 | Kalaipriya | Logical | Added metadata filter in ChromaDB vector query to exclude current bug_id from candidate duplicate matches. | 2026-09-16 | Closed | Duplicate detection successfully filters self-matches and returns accurate candidate similarity scores.
8 | Kalaipriya | 2026-09-17 | ChromaDB returns cosine distance rather than similarity, causing similarity threshold logic to incorrectly classify near-identical defects as dissimilar. | Sprint 3 | Kalaipriya | Logical | Applied normalized score formulation: similarity = 1 - cosine_distance, and calibrated thresholds: >=0.85 Likely Duplicate, 0.65-0.84 Related, <0.65 New/Unmatched. | 2026-09-17 | Closed | Similarity classification verified against benchmark duplicate evaluation pairs.
9 | Kalaipriya | 2026-09-18 | Root Cause and Remediation agents failed when ChromaDB returned no historical matches for sparse or completely novel bug descriptions. | Sprint 3 | Kalaipriya | Maintainability | Implemented defensive fallback and Insufficient Evidence handling when top similarity is below 0.35, preventing agent crashes. | 2026-09-19 | Closed | Sparse bug reports now gracefully return Insufficient Evidence with actionable prompt to user.
10 | Kalaipriya | 2026-09-20 | Suggested remediation code snippets containing special characters and markdown backticks rendered improperly in the React diagnosis report card. | Sprint 3 | Kalaipriya | User Interface | Added pre-formatted code block component with syntax highlighting, copy-to-clipboard functionality, and proper string escaping. | 2026-09-20 | Closed | Structured findings display renders remediation code snippets cleanly with verified verification checklists.
11 | Kalaipriya | 2026-09-26 | Temporal defect velocity analytics failed to compute MTTR when bugs lacked resolution timestamps or had mismatched date formats. | Sprint 4 | Kalaipriya | Logical | Added ISO-8601 timestamp parser with fallback to created_at date and zero-filled missing intervals in time-series aggregation. | 2026-09-27 | Closed | Defect velocity and chronological trend timeline render accurately across all date ranges.
12 | Kalaipriya | 2026-09-28 | Quality Gate allowed resolved bugs with empty confirmed fix code or missing component to be submitted for knowledge base indexing. | Sprint 4 | Kalaipriya | Standards | Implemented strict 6-rule validation in KBGrowthService checking description, component, error logs, root cause, resolution, and fix code. | 2026-09-29 | Closed | Quality Gate successfully rejects incomplete entries with detailed validation error messages.
13 | Kalaipriya | 2026-10-01 | Conflicting Uvicorn server processes caused port 8000 socket collisions on Windows, causing frontend requests to fail with connection refused. | Sprint 4 | Kalaipriya | Others | Terminated orphan background processes, ensured clean single-instance binding on 0.0.0.0:8000, and updated Vite proxy target to 127.0.0.1. | 2026-10-02 | Closed | Backend server runs stably and health endpoint responds with HTTP 200 OK.
14 | Kalaipriya | 2026-10-01 | Auth registration rejected non-standard email formats and usernames without @ with HTTP 422, and duplicate email registration blocked user with generic error. | Sprint 4 | Kalaipriya | User Interface | Relaxed auth schema regex to allow any username/email, and implemented frontend auto-login fallback when email already exists. | 2026-10-02 | Closed | User registration and login flow verified end-to-end; all 6 auth tests pass.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others